{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Faq"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Faq","index":0,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["N.ro","Domanda","Risposta"]
[1,"Buon pomeriggio,\r\nsiamo a richiedere un chiarimento sui tempi di esecuzione; si chiede di indicarci il valore coretto considerato che:\r\n- sul cronoprogramma allegato al progetto a base di gara (elaborato C864.L02.PE.SIC.01.KR.502) si stabilisce un tempo pari a 350 (per i primi 2 edifici) +175 (per il terzo);\r\n- sulla lettera di invito viceversa è indicato un tempo pari a 350 gg;\r\nPer cui necessitiamo di conoscere quale sia il valore corretto.\r\n\r\nIng. Virginio MOSCARIELLO","Spett.Le Operatore Economico,\r\nNell'elaborato C864.L02.PE.SIC.00.KR.502_R03 relativo al Cronoprogramma è indicato un tempo totale di 350 gg suddivisi in 175 gg per i primi due edifici (le lavorazioni si svolgeranno in parallelo) più 175 gg per il terzo edificio."]